Hospital Onboarding Plan

Interest → Prep → Kickoff → Go Live → Follow-up

Simple path to get hospitals live — without losing momentum after they say yes.

| 1 Interest | Hospital is convinced. Paperwork is done. Done when: Demo · LOI · EAA |
| --- | --- |

| 2 Preparation | Book kickoff fast so nobody is left waiting. Done when: Invite sent · Meeting booked |
| --- | --- |

| 3 Kickoff | Train the team, set up admin, finish one practice together. Done when: First practice complete |
| --- | --- |

| 4 Go Live | Hospital finishes profile. We publish. Optional first real pilot. Done when: Profile live · Pilot (optional) |
| --- | --- |

| 5 Follow-up | Stay close after launch, then move to commercial. Done when: 2w · 1m · 2m · 3m · Commercial |
| --- | --- |

| Confirm with Alex (parallel) • AI credits: free allotment, usage view, unlock / pay • Site profile: Excel import for big equipment lists • Forms: upload own forms + PDF import path | Ask 1. Approve this 5-step path 2. Assign one owner per hospital 3. Book Alex review before kickoff promises |
| --- | --- |

Day-to-day actions stay in the Excel tracker. This page is the shared plan.